## Sheet1
Issue Log
Date: 05/03/2020
Issue # | Issue Description | Impact on Project | Date Reported | Reported By | Assigned To | Priority(M/H/L) | Due Date | Status | Comments
1 | Requirements are not clearly specified | Causes delay in the project progress and scope | 2020-05-18 | Shiva Rama Krishna Vodnala | Gopichand Bandarupalli | High | 2020-05-26 | Closed | Requirements specified clearly
2 | ER diagram is not specific | Project is delayed | 2020-05-19 | Krishna Sumanth Koyyalamudi | swaroopa Tirumalareddy | Medium | 2020-05-27 | Closed | Valid ER diagram is provided
3 | Cost will be more because of the delay of the project | Budget will be exceeded | 2020-05-20 | Swaroopa Tirumalareddy | Shiva Rama Krishna Vodnala | High | 2020-05-28 | Open
4 | UI is distorted | Customer dissatisfaction | 2020-05-21 | Shiva Rama Krishna Vodnala | Krishna Sumanth Koyyalamudi | Low | 2020-06-01 | Closed | UI development fixed the issue
5 | Error in the registration page | Users cannot register to the website | 2020-05-22 | swaroopa Tirumalareddy | Krishna Sumanth Koyyalamudi | High | 2020-06-02 | Closed | Fixed the registration page error
6 | Server Issue | Server are down frequently | 2020-05-23 | Gopichand Bandarupalli | Swaroopa Tirumalareddy | High | 2020-06-03 | Closed | Fixed the server issues