## Sheet1
Risk Register for E-Pharma
Date: May 28,2020
Project Name: E-Pharma
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 1 | Executive Support | There ought to be specific commitments for the project from the highest level management. Weak government support is that the biggest risk. | Structure/Process risk | Commitment from executives |  | Risk Avoidance | Project Manager |  | High | Avoided
2 | 2 | Cash flow | Increase within the budget of the project because of many factors like raise in code worth and resources pay etc. | Financial Risk | Increase in price of softwares and resource wages |  | Risk Acceptance | Finance Manager |  | High | Anticipated
3 | 3 | Scope | The estimates of quality, dependencies and scope management is wrong or guess is wrong then there are often a large risk | Structure/Process risk | Wrong estimation |  | Risk avoidance | Project Manager |  | High | Avoided
4 | 4 | Stakeholders | In the event that partners has negative frame of mind towards a task or no collaboration between them, at that point it is a detour to the undertaking. | Process Risk | Lack of cooperation between stakeholders |  | Risk avoidance | Program Manager |  | High | Mitigated
5 | 5 | Resources and Team | In the event that the assets are leaving organization or unpracticed colleagues with appropriate range of abilities | People Risk | Lack of resources with proper skill set |  | Risk Mitigation | Project Manager |  | Medium | Anctipated
6 | 6 | Existence of similar software in the market | On the off chance that there is a comparable counseling firm that creates sites, it can diminish the notoriety of the organization | Market Risk | Availability of similar products in the market |  | Risk Acceptance | Program Manager |  | Medium | Anctipated
7 | 7 | Recession in market | Fluctuating business sector requests that reason offers to increment and diminishing with no particular example | Market Risk | Recession |  | Risk Acceptance | High |  | Medium | Anctipated
8 | 8 | Natural Disasters | Climatic conditions are wild. We need moderation intends to dodge them. | Financial Risk | Being not ready to face the risk |  | Risk Acceptance | High |  | High | Anctipated
9 | 9 | Quality | Releasing a low quality product or service that fails to meet the expected level of due diligence in your industry or that violates laws and regulations. | Compliance Risk | Lack of product testing |  | Risk Mitigation | Project Manager |  | High | Anticipated
10 | 10 | Change | The risk that change such as new technology with threaten your business model. | Strategic Risk | Change in Approach |  | Risk avoidance | Program Manager |  | Medium | Avoided